## Team Backlog
Task Name | Assignee | Progress | Expected Time | Actual Time
UART Design | Momen Hassan | DONE | 2023-05-05 | 2023-06-05
I2C Driver | Ahmed Atef | DONE | 2023-05-05 | 2023-06-05
SPI Driver | Momen Hassan | DONE | 2023-05-05 | 2023-06-05
UART Driver | Momen Hassan | DONE | 2023-05-05 | 2023-06-05
I2C Design | Ahmed Atef | DONE | 2023-05-05 | 2023-06-05
SPI Design | Momen Hassan | DONE | 2023-05-05 | 2023-06-05
Eeprom design | Ahmed Atef | DONE | 2023-05-05 | 2023-06-05
Eeprom Driver | Ahmed Atef | DONE | 2023-05-05 | 2023-06-05
ATM Application Design | Ahmed Hesham | DONE | 2023-05-05 | 2023-06-05
ATM Application Development | Ahmed Hesham | DONE | 2023-05-05 | 2023-06-05
Card Application Design | Ahmed Hesham | DONE | 2023-05-05 | 2023-06-05
Card Application Development | Ahmed Hesham | DONE | 2023-05-05 | 2023-06-05
Application Testing | Team | DONE | 2023-05-05 | 2023-06-05

## Test Cases Sheet
Test Case ID | Description / steps | Expected Results | Actual Results | Progress
CARD
1 | Pressing all inputs before getting the trigger signal |  |  | PASS
2 | Entering wrong pin three times |  |  | PASS
3 | Entering invalid PIN length |  |  | PASS
4 | Entering correct pin |  |  | PASS
ATM
1 | Enter PAN > 19 numeric characters |  |  | PASS
2 | Enter PAN < 16 numeric characters |  |  | PASS
3 | Enter PAN with alphabetic characters |  |  | PASS
4 | Enter Correct PAN |  |  | PASS
5 | Enter PIN > 4 numeric digits |  |  | PASS
6 | Enter PIN < 4 numeric digits |  |  | PASS
7 | Enter PIN alphabetic digits |  |  | PASS
8 | Enter different PINs in confirmation |  |  | PASS
9 | Enter Correct PIN |  |  | PASS
10 | Enter correct PIN confirmation |  |  | PASS
Application
1 | Approved User Story Mention balance before the transaction |  |  | PASS
2 | Fraud Card |  |  | PASS
3 | Stolen Card |  |  | PASS
4 | Max limit exceeded |  |  | PASS
5 | Insufficient fund |  |  | PASS